CHAPTER 6.   TYPES OF CONTRACTS, CLAUSES, AND CONTRACT

ADMINISTRATION

Section 1.   Pricing Arrangements and Contract Options

6-1 .  CONTRACT TYPES.

A. General.

1. One of the most important factors in successful procurement is the

selection of an appropriate contract type. The contract type sets the pricing arrangement and incentive structure for the contractor and guides the performance of the contract. Therefore, the contract type should give the contractor an incentive to perform efficiently the required work. The Contracting Officer is responsible for deciding which contract type to use; however, if the competitive or noncompetitive proposals method of procurement is used, the contract type is a matter for negotiation with the contractor. In most cases, the housing authority should rely on firm-fixed- price contracts, because the pricing arrangement poses the least risk to the housing authority, as described below. Regardless of the procurement method, each solicitation should state clearly what contract type will be used. The following sample statement may be used, and should be included in a prominent place in the solicitation:

TYPE OF CONTRACT

The Housing Authority of the City of Elizabeth contemplates the award of a ___________________ (insert specific type) contract resulting from this solicitation.

2. The selection of a contract type also has a bearing on the amount of competition that will be received. The Contracting Officer should select the contract type that will promote maximum competition, consistent with the adequacy of the housing authority’s description of its needs.

3. The most crucial consideration in selecting the contract type is the amount of risk shared by the parties. In a fixed price contract, the contractor bears the risk of performing the work at a cost greater than anticipated. In a cost reimbursement contract, if the work is not completed by the contractor devoting his best efforts, the housing authority bears the risk and must pay the contractor more money if the work is to be completed.

B.  Basic Categories.   There are two basic categories of contract types fixed price and cost reimbursement.

1.  Under a fixed price contract, the contractor must deliver the product or perform the service for the price agreed on, regardless of the cost incurred.

2.   In a cost reimbursement contract, the contractor agrees to expend its best efforts to achieve the specified requirement, within the estimated amount established in the contract. If the contract is not fully performed in the time the contractor expends the funds, then the contractor has no obligation for further performance unless the contract is modified to increase the funds.

C.   Factors Influencing Contract Type.

1. The most important factor influencing the choice of contract type is the description of what the housing authority is buying. Requirements that are complex and unique to the housing authority, which have a likelihood of changes in the technical direction and performance uncertainties, normally place greater risk on the housing authority. If a need is of particular urgency, it may also require the housing authority to assume a greater proportion of risk, or the contract should contain incentives to ensure timely performance. Contracts extending over a relatively long period of time may require a contract type that allows economic price adjustment. Market conditions may also affect the type of contract selected, as unstable conditions may require the housing authority to assume more risk than in a stable market situation.

2. The preferred contract type for most housing authority procurements is firm fixed price.  This approach provides for maximum incentive for the contractor to manage cost efficiently, and places less burden on the housing authority in administering the contract. There are, however, some inherent risks in using fixed price contracts. If the housing authority has not described its needs in accurate and precise terms, resulting in ambiguous specifications, contractors may factor in contingencies in their offers to cover such uncertainties, thus producing unrealistic price proposals. If the housing authority’s needs are not fully defined when the solicitation is issued, there may be a continual re-defining of needs during contract performance, which is ill-suited to fixed price contracting. These problems can be avoided by emphasizing to the A/E and/or other consultants the need to fully and accurately define its needs.

D. Specific Contract Type.   Each solicitation and contract shall contain a clause identifying the specific contract type used. In addition, the Contracting Officer should prepare a written justification if a cost-reimbursement type of contract is selected. The justification should be included in the contract file, outlining the reasons why the preferred fixed-price type is not feasible. This is necessary to document the reasons why the housing authority is using a contract type which may be more costly to the housing authority than the fixed price management.

[24 CFR 85.36 (b)(9)]

E. Other Considerations.   If the sealed bidding method is used, only a firm fixed price or fixed price with economic price adjustment contract type may be used. When contracting by competitive or noncompetitive proposals, any other contract type is permissible. In special cases, a combination of contract types may be advantageous; however, it is essential that their application be clearly defined and that the means for administering the combination-type contract is readily available. Other contract types are available in addition to those described above, but the housing authority should avoid selecting a contract type that is too complicated for its needs. [24 CFR 85.36 (d) (2) (iic) (D)]

F. Prohibited Contract types. The following contract types are prohibited by the common rule on grantee procurement. [24 CFR85.36 (f)(4)].

- Cost plus a percentage of cost. This type of contract is prohibited,

because it would bind the housing authority to pay costs to be incurred in the future but undetermined at the time the contract is awarded, plus a commission based on the percentage of such future costs. In such a contract, the contractor’s profit increases in proportion to its costs incurred in the performance of the contract, which provides no incentive for controlling costs.

2.   Percentage of Construction Cost. Under this method, cost for

individual construction related services is determined by applying a percentage of actual construction costs as a fee, such A/E contract in which the fee is determined based on the total construction cost. Such arrangement encourages the contractor to design an overly expensive construction job.

6-2  OPTIONS.

A. General.  In many cases, the housing authority may need to acquire supplies, services, or construction which the housing authority knows will be required for more than just the housing authority’s immediate needs. One method of obtaining firm commitments from contractors for additional quantities or services is to include an option clause in the contract when purchasing the housing authority’s initial needs. The advantage of awarding a contract with options is that it gives the housing authority a continued source for supply under contract, as known prices.

B.  Definition. An option is a unilateral right of the housing authority to order additional supplies, services, or construction at the prices specified in the contract. A clause which allows an option to be exercised only at the contractor’s direction is not an option; instead, that is tantamount to a new procurement, and such clauses shall not be used.

C.  Limitations.

- An option may only be exercised if the basic contract stated a price for

the supplies, services, or construction. An unpriced option, like a bilateral option, is considered a new procurement. In the case of a cost reimbursement contract, an estimated cost for the option period should be negotiated and included in the basic award.

- A further limitation is that options may not continue indefinitely, there

must be a finite period for the contract, including all options, and a specific limit on the total quantity to be purchased by option.

- Any contract containing options must specify the time by which the

housing authority must exercise the options. The housing authority should allow itself enough time to ensure that funds will be available and a management decision made as to the need for the option quantities. Nevertheless, the housing authority does not have an indefinite amount of time to exercise an option, because contractors should not be left in doubt for an extended period of time regarding whether their contract options will be exercised. In order to avoid confusion and/or disputes, the housing authority should specify in the contract the housing authority has up to 30 days after contract expiration to exercise any remaining option which was included in the original contract.

- Since options establish a long-term relationship with a single supplier,

they should be used with caution and should not be exercised unless there is a clear and obvious reason. For example, the contract is for a very large quantity and substantially lower prices are available compared to smaller quantity purchases. In this case, use of options is clearly advantageous. Alternatively, if prices are expected to be falling or very competitive for an item widely sold in the commercial market, it may be to the housing authority’s advantage not to include many options in contracts, since better prices may be obtainable by conducting a new procurement for future needs. If the housing authority decides to include options in a solicitation, the options should be evaluated as part of the contract award, to ensure that the evaluation takes into account the total eventual cost of the entire contract.

D.  Exercising Options.  Before exercising an option, the

housing authority should document the contract file with a

written determination, which should include the following: [24 CFR 85.36 (b) (9)]

- Funds availability;

- Statement as to continuing need for the item;

- Indication as to whether the option was included and evaluated as part

of the basic contract;

4. Review of market prices to indicate whether the option is still

economical for the housing authority; and

5. Any other factors (such as time or disruption to the housing authority’s

operations) supporting the housing authority’s decision to exercise the option.

E. Clauses.   Sample option clauses are provided below:

OPTION TO EXTEND THE TERM OF THE CONTRACT

The housing authority may extend the term of this contract for the period specified herein, by written notice to the contractor by the expiration date of this contract or within 30 days after funds are made available for exercising the option, whichever is later. The total duration of this contract, including all options, shall not exceed                   (months) (years) (days).

OPTION FOR ADDITIONAL QUANTITIES

The housing authority may order additional quantities as specified in this contract at the prices specified for the options. The housing authority may exercise the options by written notice to the contractor by________ (date) . Delivery of options items shall continue at the same rate that like items called for under the contract, unless the parties otherwise agree.

Section 2   Provisions and  Clauses

  - SOLICITATION PROVISIONS.   Solicitation provisions are designed to provide information to prospective contractors about the solicitation stage of the procurement process. Terms and conditions which apply to the contract upon award are referred to as contract clauses. The Forms HUD-5369 and HUD-5369-A contain provisions to be included in all solicitations for construction work. For non—construction procurements, forms HUD-5369--B and HUD-5369-C must be used. It may be useful to request that bidders provide samples of their products for a supply contract. In such case, a provision similar to the following should be included in the invitation for bids: [24 CFR 85.36 (1); 905.185]

BID SAMPLES

Samples of items, when required, shall be furnished free of expense prior to the opening of bids. Samples received from the successful bidder will not be returned. Samples received from unsuccessful bidders, upon request, will be returned at the bidders’ expense.

6-4  CONTRACT CLAUSES.

A.  HUD Forms.  There are several clauses required by 24 CFR 85.36(i) that are required to be included in all housing authority contracts. Form HUD-5370 contains clauses to be included in all contracts for construction work, while Form HUD-5370-A includes clauses necessary for non-construction contracts, and A/E contract clauses are included in Form HUD-519l5.1 for development and form HUD-5l9l5A for modernization. Use of these forms is mandatory for housing authorities.

B. Other Clauses. Other clauses that should be included in housing authority contracts in specific circumstances, as needed, are described in Exhibit 8.

Section 3.  Contract Administration

6-5  GENERAL.  Frequently, contract administration is the most ignored area in procurement. The urgency of making the contract award often makes post-award issues seem of little concern. Nevertheless, without effective contract administration and monitoring of contract performance, the efforts made in awarding the contract may be wasted. The amount of oversight and monitoring will vary with the complexity of the work. Relatively simple contracts may only require limited monitoring. The following procedures are designed to help ensure that proper attention is given to contract administration to provide the housing authority with the greatest value for its contract dollar, particularly for more complex purchases.

A.  Planning For Contract Administration. Effective management of contracts requires proper planning of both housing authority and contractor activities to achieve meaningful results. Relatively simple contracts (e.g., the purchase of office supplies) will not require any significant planning. For more complex contracts, however, it is advisable to develop a formal, written contract administration plan before contract award. This document spells out the responsive duties of the various housing authority offices and departments in a larger housing authority that would be involved and provides procedures for regular status reports and progress meetings.

B.   Post-Award Conference and Notice to Proceed.

1.  Following the award of a construction contract, a

preconstruction/safety conference should be held for discussing all construction and contract administration related issues. Then, a Notice to Proceed should be issued by the housing authority to the contractor stating the starting and completion dates and typical contract related information. The notice should be sent by registered mail, return receipt requested. If desired, the notice may be prepared in an original and at least two copies signed by the Contracting Officer, to be sent by registered mail, return receipt requested. The contractor should retain the original and sign, date, and return the copies.

2. For large non-construction contracts, it may be desirable to meet with

the contractor soon after contract award to ensure that both parties understand what is expected of them in the performance of the contract.

3. Any changes to the contract that are necessary as a result of any post-

award conference should always be reflected in a formal modification to the contract; otherwise, the contractor will be held to the strict wording of the contract, rather than any oral agreements or instructions from housing authority staff.

6-6   RECEIPT

A.  General. The housing authority shall establish a system for ensuring that the items required by contract are delivered to an appropriate location where the housing authority can ensure that receipt of contracted items is properly handled and documented. I.E. example, a contract for supplies should indicate where (what room, or other location, such as a warehouse or loading dock) delivery should be made, and how acknowledgment of receipt will be recorded and provided to the contractor.

[24 CFR 85.36  (b) (2)  &  24 CFR 905.160  (b)]

B. Form. The housing authority should use a standard receiving report to document receipt, inspection, and acceptance.

The report should contain, as a minimum the following information:

Contract Number

Item Number

Description of Item

Date of Receipt

Place Received

Receiving Official (printed name, signature, and date)

Date of Inspection

Inspecting Official (printed name, signature, and date)

Whether the work/item was or was not accepted

If not accepted, reasons for rejection

Accepting Official (printed name, signature, and date)

6-7  MONITORING INSPECTION. [24 CFR 85.36(b) (2) & 905.160 (b)]

A. General.

- Receiving quality goods and services has a material impact on the

housing authority operations as well as the lives of the residents. Failing to ensure receipt of the best value for the funds spent costs the housing authority additional money, lost staff time and delayed delivery of the completed product. Consequently, it is a critical duty of the housing authority to ensure that it receives quality products. In order to achieve this objective, the housing authority must first ensure that it contracts highly qualified A/E firms to design and inspect proposed contract work. The housing authority must then take an active role in holding the A/E firms accountable for the delivery of complete and superior designs. The housing authority must further hold the A/E firm accountable for not only carrying out the necessary inspections and monitoring, but equally important, ensuring that quality of the work performed by contractors meets industry standards and is consistent with the plans and specifications of the contract. If a housing authority does experience poor performance, it should consider that performance when awarding future contracts. It should also make recommendations to HUD, when appropriate, regarding suspensions and debarments and provide evidence involving serious complaints, non-responsibility, and other violations and failures to the HUD Field Office for review (see Chapter 5 - Contractor Qualifications and Duties).

2. While there are numerous promises made and duties

assumed by a contractor under the wide variety of housing authority contracts presently used, the heart of performance problems is in either the technical requirements of the contract or in the time for performance. Much of the difficulty in the technical area is involved with the interpretation of specifications. There is no assurance that the articles delivered under a contract will meet those specifications. Whether or not the housing authority inspects, accepts, rejects, or takes some other actions with respect to work performed will in all probability seriously affect its rights against the contractor. Monitoring the contractor’s performance against the time when the performance is required is also an important part of contract administration.

3. The housing authority shall keep an effective control on all

unfilled orders and available obligated funds by maintaining suspense files until deliveries are made. Payment for supplies and services is made only after the delivered item is inspected and found to be satisfactory. This helps to eliminate disputes that arise when shortages or damages are not discovered until after the payment has been made.

4. In addition, for construction and maintenance contracts, the

housing authority is also responsible for monitoring compliance with labor standards requirements as provided in HUD Handbook 1344.1 REV I or as applicable to maintenance contracts

B. Timing.

- In order to ascertain that the housing authority gets what it is

paying for, it shall inspect the contractor’s work, and enforce compliance with the contract specifications. This is especially important since the rules of law and the contract

language may, in certain instances, relieve the contractor of liability for defects if the housing authority did not require correction before final acceptance. The housing authority is not obligated to pay for or accept goods or construction until it has had an opportunity to inspect them. Such inspection, and any rejection resulting there from, shall be within a reasonable time after delivery. If the housing authority fails to require the contractor to correct a particular defect because of failure to inspect, when such defect could have been found by reasonable inspection, the housing authority may have waived its rights to future rejection based on that particular defect.

2.   Acceptance may be assumed to have occurred, with or without concurrence by the housing authority, after a reasonable time to inspect the goods or construction has passed, and the housing authority has failed to make any notification to the contractor that the goods or construction do not conform to the contract requirements. The housing authority must pay at the contract rate for any goods and construction accepted.

C.  Construction Contracts.

1. General.

a. The housing authority shall meet with its architect and the contractor on

a regular basis to discuss work progress. any problems or deficiencies noted during inspection visits, overdue reports and the construction schedule. The housing authority should prepare a written record of the items discussed at each meeting and place a copy in its construction file. The quality of the inspection of the work is critical and the housing authority must assure that either the A/E or the designated person responsible for inspection is fully qualified and performs the inspections frequently and thoroughly.

b. Upon being notified by its architect of construction deficiencies, the

housing authority shall promptly notify the contractor in writing of the deficiencies observed. This notification also shall advise the contractor that failure to make timely corrections would be an infraction of the contract and that the contractor is liable for any resulting losses or delays.

c. The housing authority is also responsible for performing required

warranty inspections, including the 11-month inspection required for CFP, during the warranty period and promptly notifying the contractor in writing to remedy any defects relating to manufacturer or contractor warranties on equipment and systems and contractor warranties on materials and workmanship. The contractor is responsible to pay for any damage to other work resulting form such defects.

- Progress Payments.

CFP and development payments shall be made as follows:

(1) Where progress payments are necessary, the housing authority shall require the contractor to prepare a construction progress schedule for each project immediately after housing authority issuance of the notice to proceed, use format acceptable to the PHA.. The information shall be realistic and consistent with the information provided by the contractor on the housing authority—approved schedule of amounts for contract payments and the HUD-approved Project Implementation or Development Schedule, as applicable.

(2)  The housing authority or its architect under contract shall review the contractor’s construction progress schedule to determine that the scheduled dates and amount of work to be completed are reasonable and consistent with the contract. If acceptable, the housing authority architect shall sign the schedule and forward it to the housing authority for approval. Upon approval by the housing authority, the approved construction progress schedule shall be returned to the contractor.

(3)  The housing authority shall require the contractor to prepare a schedule of amounts for contract payments immediately after execution of the contract. The housing authority shall use Form HUD-5l000, Schedule of Amounts for Contract Payments.

(4)  The housing authority and its architect shall review the schedule to determine that the scheduled work to be completed by the specified dates and the amount of payment for such work are reasonable. If acceptable, the housing authority shall approve and return the schedule to the contractor. Field Office review is not required.

(5)  The housing authority is responsible for making progress payments to the contractor based on the housing authority—approved schedule of amounts for contract payments. Generally, progress payments for acceptable work and materials delivered and stored on the site are made at 30—day intervals. Field Office authorization of progress payments, based on the approved payment schedule, is not required.

(6)  The contractor shall submit a request for payment for each project on Form HUD-5100l, Periodical Estimate for Partial Payment. The request shall be accompanied by the contractor’s written designation of certifying officer. In addition, the contractor shall submit the following HUD forms or other

appropriate forms, if applicable, with each periodical estimate for partial payment: Form HUD-51002, Schedule of Change Orders; Form HUD-51003, Schedule of Materials Stored; and Form HUD-51004, Summary of Materials Stored.

(7) The housing authority shall review each contractor request and shall approve the payment if the following conditions have been met; if the contractor requests payment for items which have not been acceptably completed, the housing authority shall delete those items and adjust the payment accordingly.

(a) the contractor request is consistent with the housing authority—

approved schedule of amounts for contract payments:

(b) the request does not include the amount to be retained by the housing

authority under the contract;

(c) the work covered by the payment has been performed in accordance

with the construction documents;

(d)  the Form HUD—5l001, Periodical Estimate for Partial Payment, has

been properly executed and all applicable supporting documentation submitted; and

(e) the contractor has submitted all required reports, such as payroll

reports.

The housing authority shall retain the original Form HUD-5l001 and any applicable supporting documentation for its file and return a copy of the housing authority-approved forms to the contractor.

3. Time Extensions.

- The contractor is responsible for completing the work within the time

established in the contract. The housing authority is responsible for monitoring the contractor to ensure that work will be completed as scheduled. The housing authority may authorize justifiable time extension without prior Field Office review and approval. The “Default” clause on the Form HUD—5370 prescribes the conditions under which a time extension may be granted. The basic principle is that delays arising from unforeseeable causes beyond the control and without the fault or negligence of the contractor may be grounds for allowing a time extension. Such time extension should be formalized in a written modification to the contract.

b.  Construction Log

(1) The housing authority shall maintain a construction log to record

potential causes for delays which may be used as the basis for granting time extensions or for determining the amounts of liquidated damages to be assessed against the contractor. The housing authority shall maintain a record of the following:

(a) the daily temperature;

(b) the daily amount of precipitation;

(c) delays in obtaining labor and materials, including the duration

and reason;

(d) labor disputes or strikes, including the duration and the

applicable construction trade;

(e) delays experienced by others in completing non contract public

improvements (whether on-site or off-site) ; and

(f) other causes for delays, such as fires, floods, vandalism or court

orders.

(2) In order to be considered for approval by the housing authority,

requests for time extensions must meet the following criteria:

(a) the contractor must have submitted a written notice to the

housing authority within 10 calendar days of the start of any delay; and

(b) the severity and extent of adverse weather could not have been

reasonably foreseen by the contractor (normal seasonal levels of rain, snow, cold or heat should have been considered by the contractor) or the cause of the delay was beyond the contractor’s control.

4. Documentation. Immediately upon receipt of the contractor’s

notification of delay or request for time extension, the housing authority shall send a letter of acknowledgment to the contractor. The letter shall indicate that: immediate consideration will be given to the contractor’s request; or the actual delay in work is difficult to determine and consideration will be given to the contractor’s request upon completion of work. The housing authority shall review its records to ensure that the

information provided by the contractor is accurate, to determine the cause of the delay and the extent that it was within the contractor’s control, and to ascertain if the request meets the criteria established above. Based on its review, the housing authority shall prepare a “finding of fact” with the assistance of its architect and attorney and, in order to approve, determine that: [24 CFR 85.36 (b) (9))

- the contractor’s request, as documented by the housing authority

“finding of fact,” meets the requirements stated above; and

b. the additional time requested by the contractor is reasonable based on

the nature and duration of the delay.

5. Warranties.

a. The warranty period for all construction work shall be at least 365 calendar days from the date of final acceptance of the work in question, or such longer period as otherwise specified in the control. The housing authority is responsible for performing required warranty inspections, including the 11— month inspection, during the warranty period and promptly notifying the contractor in writing to remedy any defects

relating to manufacturer or contractor warranties on equipment and systems and contractor warranties on materials and workmanship.

This is an area which is frequently overlooked by housing authorities and their A/Es. Failure to enforce warranties is not only a violation of the ACC, but is very costly to the housing authority. In such cases, the housing authority will have to use its own funds after the expiration of the warranty to correct defects that were the contractors responsibility.

b. Upon receipt of the housing authority written notice, the contractor shall promptly remedy any defects due to the use of faulty equipment or materials, or poor workmanship. The contractor also is responsible for paying for any damage to other work resulting from such defects.

6. Completion 21 Work.

a. Notification. The contractor shall provide prompt written notification to the housing authority when all work is completed. Until the final inspection has been made, the housing authority shall not advance any of the retainage or make the final payment to the contractor.

b. Final Inspection. Upon receipt of the contractor’s notification of the date when the work had been completed, the housing authority shall conduct a final inspection within 10 calendar days. The final inspection shall be conducted by: a housing authority representative; the housing authority architect, where applicable; and a contractor representative.

c.  Post-Inspection Meeting. The inspection team shall meet after completing the final inspection to determine whether; the work has been completed in accordance with the construction documents; there are any minor items of incomplete or unsatisfactory work (or seasonal work such as planting of shrubs

and lawns) and reach agreement on the items to be included on the ( housing authority’s or its architect’s final punch list; or there are any major deficiencies which must be corrected by the contractor so that another final inspection can be made before contract settlement.

d. Documentation. Following final inspection, the housing authority shall notify the contractor to submit the following to the housing authority:

(1) Where appropriate, a certificate of occupancy issued by the responsible

local agency for each building;

(2) One notarized original and two copies of the contractor’s release and

certification which includes:

- the work completed in accordance with the construction

documents, including contract modifications, except any minor items identified on the housing authority’s or its architect’s proposed certificate of completion;

(b) the total amount due the contractor and a separately stated

amount for each unsettled claim against the housing authority;

(c) the housing authority is released of all claims, other than those

stated in the contractor’s release; and

(d) wages paid to laborers or mechanics were consistent with the

wage rate requirements of the contract and there are no outstanding claims for unpaid wages.

(3) Assignment of all Guarantees and Warranties to the housing authority; and

(4) “Final” Partial Payment. The housing authority may accept part of a

project for occupancy before contract settlement where the following conditions are met:

(a) The dwelling units to be accepted (except items approved for

delayed completion) have been completed and are ready for occupancy.

(b) The general contractor agrees to early occupancy and

completion of items approved for delayed completion.

(c) Early occupancy will not unduly inconvenience or ( represent a

safety risk to tenants while the unfinished work is  being completed;

(d) The housing authority has obtained permits from the responsible local agency for each unit to be accepted; and

(e) The housing authority has executed an occupancy agreement with the

general contractor indicating that the housing authority partially accepts the specified work provided that the contractor accepts the responsibility to complete the project by the estimated completion date.

7.  Final Payment.

a. The housing authority shall ascertain that an adequate and

notarized certificate and release are received from each construction contractor to assure that the work was in full compliance with the construction contract documentation, and that all material, supply, equipment and labor related expenses have been paid in full by the contractor.

b.  The housing authority payment to the contractor shall be the

amount  specified in the certificate of completion and shall not include any amount to be retained for disputed items and incomplete work, such as punch list or seasonal items.

D. Report.

1. All progress inspections should be documented using an appropriate

housing authority property inspection report. The inspection report should include a description of the work or service completed and a determination as to whether or not the work or service is acceptable. If payment is made on a unit price basis, quantities must be verified. If payment is made on a time and material basis, the report should know that the time charged was spent on housing authority work, services, or supplies and that materials were charged at cost. A copy of the inspection report should be included in the contract or purchase order file. Based on the progress report, the Contracting Officer should initiate any needed follow—up actions to ensure that the terms of the contract will be fulfilled.

2. In general some of the specific tasks the housing authority may consider

are: visiting the contractor’s place of performance; comparing actual performance against scheduled performance; observing any adverse conditions (such as labor problems, overextension of facilities, equipment idle or needing repair, changes in key staff, etc.); interviewing staff to determine if the skill level is sufficient to perform the assigned tasks.

The housing authority must also ensure that the quantity and quality of supplies and materials are adequate. The housing authority should test the materials to insure that they are at the required level of quality and count the inventory to assure that the appropriate amount is received.

6-8 ACCEPTANCE.

A. General.  The Executive Director or the Contracting Officer shall ascertain that supplies received from vendors are inspected and acceptable, that the performance was satisfactory (for services) , and that receiving documents are prepared and processed for payment. This acceptance should not be delayed, since prompt payment will help to ensure good relations with the public. In addition, many contracts allow a discount for prompt payment if made within a specified number of days. Discounts, if offered by the contractor, should always be taken by the housing authority to the greatest extent possible, and procedures should be established to facilitate expected receipt and prompt payment. [24 CFR 85.36 (b) (2) & 905.160 (b)]

B. Nonconformance.

- When goods or some construction items do not conform to the

contract, three are basically three choices. First, the housing authority may reject the items; second, it may require the contractor to correct them; and third, it may conditionally accept them. Ordinarily, contractors will be given an opportunity to correct the defective items.

. 	2. If the items are rejected, the contractor is subject to being declared in default unless it can furnish conforming items or make correction within the required delivery schedule/completion time. If the contractor is required to correct the defects, it would appear that the housing authority has elected to have them corrected and may not, therefore, terminate the contract for default until the contractor has had a reasonable opportunity to correct the defects. If the contractor does not correct the defects within the required schedule, the housing authority may require delivery/completion of the uncorrected items and negotiate a reduction in the contract price.

3. The choice of which action to take under the circumstances is within the

Contracting Officer’s discretion. Corrective actions by the contractor shall be requested by the housing authority in the form of registered or certified letter return—receipt requested.

6-9  ALLOWABLE COSTS.

A. General. For cost reimbursement contracts, the housing authority must be vigilant in reviewing the vouchers or invoices submitted by the contractor to ensure that only allowable costs are charged and paid. Cost allocability for profit-making firms shall be determined in accordance with HUD regulations.. For contracts with nonprofit organizations, the cost principles in 0MB Circular A-122 shall apply; for contracts or agreements with State and local governments, the cost principles in 0MB Circular A—87 apply. [24 CFT 85.22; 85.36(f) (3)]

B. Contract Clause. Accordingly, the following clause should be included in all cost reimbursement and any other contacts that contain a cost reimbursement portion:

ALLOWABLE COSTS

1. The housing authority shall make payments to the contractor at the times specified elsewhere in this contract, in amounts determined to be allowable by the Contracting Officer in accordance with Subpart 31.2 of the Federal Acquisition Regulation (if the contractor is a for-profit firm; or 0MB Circular A-l22 for nonprofit organizations, or 0MB Circular A-87 for State and local governments, including Indian tribal organizations) in effect on the date of this contract and the terms of this contract.

2. Allowable costs include only those recorded costs that, at the time of the request for reimbursement, the Contractor has actually paid for items or services directly for the contract; costs incurred but not necessarily paid for materials issued from the contractor’s inventory and placed in use on the contract; direct labor; direct travel; other direct in-house costs; and properly allocable and allowable indirect costs, as shown in records maintained by the contractor for purposes of obtaining reimbursement under housing authority contracts; and the amount of progress payments paid to subcontractors under similar cost standards.

3. At any time before final payment, the housing authority may have the contractor’s invoices or vouchers audited. Any payment may be reduced by amounts found by the housing authority to constitute unallowable costs or adjusted for prior overpayments or underpayments. The housing authority may at any time issue to the contractor a written notice of intent to disallow specified costs incurred or planned for incurrence under this contract that have been determined to be unallowable under the contract terms, and the contractor may submit a written response to the housing authority with justification for allowance of the costs. If the contractor does respond within 60 days, the housing authority shall, within 60 days of receiving the response, either make a written withdrawal of the notice of issue a written decision. Failure to issue a notice under this clause shall not effect the housing authority’s right to take exception to incurred costs.

C. Limitation of Cost. Cost reimbursement contracts must also contain a limitation of cost clause requiring the contractor to notify the housing authority before the estimated cost is reached.

6-10 CONTRACT MODIFICATIONS.

A. General. Occasionally, it is necessary to modify a contract or purchase order to reflect changes in the required effort. Contract and purchase order modifications shall be issued in one of the following modification forms:

1. bilateral modification (such as a supplemental agreement, in which both parties mutually agree on contract changes) that is signed by both the Contracting Officer and the contractor; or

2. unilateral modification (a modification that is signed only by the Contracting Officer, such as a change order pursuant to the Changes clause on Form HUD—5370, or administrative modification, such as a change in the address of the payment office).

Bilateral modifications are the preferred method of modifying contracts and purchase orders. In either case, all contract modifications shall be in writing.

B. Change Orders.

- A change order is a change issued by the Contracting Officer, after the award of a contract, in any of the contract terms, including specifications, completion time,

- description of the work, etc., within the scope of the contract. All housing authority contracts shall contain a Changes clause, such as that on the Forms HUD-5370 (for construction) or HTJD-537O-A (for non construction) . A change order may be issued unilaterally by the Contracting Officer. In such cases, the contractor is entitled to submit a change order proposal to identify any changes in cost or schedules as a result of the change, and the parties negotiate an equitable adjustment.

2. Change orders may be issued bilaterally if the contractor will agree to the change in advance. When a change is mutually agreed upon, including price adjustment for concessions made by either party, a contract modification document is prepared and signed by both parties to the original contract. Change Orders shall include at least the following:

a. a detailed description of the proposed change in work;

b. a reference to the applicable working drawings and specifications;

c. a fixed price (credit, debit, or no change) for the change in contract work;

d. estimate of any additional time, if any, required to complete the work.

e. the contractor’s itemized breakdown of the cost of materials and labor and an itemized breakdown for any applicable subcontractors ; and

f. the change indicated on the architectural or engineering drawings, if applicable.

C. Limitations on Change Orders. There are limitations on the use of change orders. The Changes clause prescribes the specific circumstances in which a change order may be issued. Changes such as increasing the number of items being purchased or other types of new work are not considered within the scope of the contract or within the authority of the Changes clause.

D. Records.  The housing authority shall accurate records and docuxnentation regarding contract modifications by including a register in each contract file. This is required to provide a permanent record of all actions taken in connection with each contract. To provide an overview of all contract modifications and for tracking purposes, the housing authority should consider maintaining in the contract file a register of modifications to identify: [24 CFR 85.36(b) (9)]

1. the number of the modifications;

2. a brief description of the modification;

3. the cost of the proposed modification;

4. the date submitted to the HUD Field Office for approval, if applicable;

5. any critical deadline dates that must be met by the Field Office

6. if applicable, the date of Field Office approval or disapproval and the action taken; and

7. the amount of any additional time required by the contractor.

6 - 11 CONTRACT TERMINATIONS. [24 CFR 85.36 (i) (2)]

A. General.  The Contracting Officer may terminate a contract or purchase order for default for any of the following reasons: failure to deliver the supplies, services, or construction as specified; failure to perform work in a timely manner; violation of a contract clause, such as the prohibition against gratuities; repeated violations of labor standards; and similar reasons. Contracts are terminated for reasons described in the termination clauses on Forms HUD-5370 and revised 5370-A. The default clause provides for termination without negotiation when the contractor fails to perform as specified in the contract. Contracts terminated for the convenience of the housing authority likewise require immediate work stoppage, but termination costs are negotiated until a satisfactory settlement is reached.

B. Termination Notice.  The Contracting Officer shall terminate contacts for convenience or default only by a written notice to the contractor. The notice shall be sent by certified mail, return receipt requested. The notice shall state the following:

1. that the contract is being terminated for the convenience of the housing authority or for default, under the contract clause authorizing the termination;

2. whether the contract is terminated in whole or in part; for partial terminations, identify the specific items being terminated;

3. if terminated for default, the acts or omissions constituting the default, the Contracting Officer’s determination that failure to perform is not excusable, the housing authority’s right to change excess costs of reprocurernent to the contractor, and the contractor’s appeal rights;

4. the effective date of termination;

5. the contractor’s right to proceed under the unterminated portion of the contract; and

6. any special instructions.

Copies of the notice should be sent to the contractor’s surety, if any, and any assignee.

C. Termination for Convenience.

1. Settlement. Settlement of contracts terminated for convenience shall be handled by negotiated agreement or deterininationby the Contracting Officer. The contractor shall submit a settlement proposal promptly to the Contracting Officer for the amount claimed as a result of the termination. Whenever possible, the Contracting Officer should negotiate a fair and prompt settlement with the contractor and settle a settlement proposal by determination only when it cannot be settled by mutual agreement.

2. Compensation. A settlement should compensate the contractor fairly for work done and the preparations made for the terminated portions of the contract, including a reasonable allowance for profit (but no profit shall be allowed for settlement expenses) . However, the Contracting Officer shall not allow profit if it appears that the contractor would have incurred a loss had the entire contract been completed. Fair compensation is a matter of judgment and cannot be measured exactly. The Contracting Officer should use the prudent business judgment in the settlement process, as opposed to strict accounting principles. The parties may agree to a total amount to be paid to the contractor without agreeing on individual cost items or profit.

D. Termination for Default.

1. General.  A contract may be terminated for default because of the contractor’s actual or anticipated failure to perform its contractual obligations. Under a termination for default, the housing authority is not liable for he contractor’s costs or undelivered work and is entitled to the repayment of progress payments. If the contractor fails to make progress so as to endanger performance of the contract, the Contracting Officer shall give the contractor a written notice specifying the failure and providing a period of 10 days (or longer period if needed) in which to cure the failure. Upon expiration of the 10 days (or longer period) , the Contracting Officer may issue a notice of termination for default, unless the failure to perform has been cured.

2. Notice.  If the contractor has failed to perform work within the required time, and a termination for default appears appropriate, the Contracting Officer should, if practicable, notify the contractor in writing of the possibility of termination. This notice shall call the contractor’s attention to the contractual liabilities if the contract is terminated for default and request the contractor to show cause why the contract should not be terminated by default. If the response to this notice is inadequate or insufficient actions is taken in response to it, the contract may then be terminated for default.

3. Alternatives.  Alternatives to termination for default, at the housing authority’s discretion, include the following: allow the contractor or the surety to continue performance of the contract under a revised delivery schedule (in exchange for a reduced price or other consideration); permit the contractor to continue performance of the contract by means of a subcontract or other business arrangement with an acceptable

third party, provided the rights of the housing authority are adequately protected; or if the requirement for the supplies, services, or construction no longer exists, and. the contractor is not liable to the housing authority for damages, execute a no— cost termination settlement agreement.

4. Repurchase. When the supplies, services, or construction are still required after termination, the Contracting Officer shall repurchase the same or similar items against the contractor’s account as soon as possible. The Contracting Officer may use any appropriate procurement method for the repurchase (sealed bidding, competitive proposals, or noncompetitive proposals) , provided that competition is solicited to the maximum extent practicable to secure the lowest price obtainable under the circumstances, in order to mitigate damages.